## Projects
project_id | project_name | owner | stage | status | progress | start_date | release_date | priority | client | tags | notes
PRJ-001 | Acme Corp Website | Zoe F. | Development | delayed | 9 | 2026-01-31 | 2026-04-12 | High | Acme Corp | React, AI, Multi-tenant
PRJ-002 | Nimbus Health Patient Portal | Elif D. | QA | at_risk | 66 | 2026-03-16 | 2026-04-27 | High | Nimbus Health | B2C | Designs signed off — implementation in progress.
PRJ-003 | Orbital Labs Admin Dashboard | Zoe F. | Development | at_risk | 25 | 2026-03-27 | 2026-04-30 | Medium | Orbital Labs | AI, GDPR | Third-party API rate limits being reviewed.
PRJ-004 | Ironclad Finance Mobile App | Sarah K. | Planning | delayed | 5 | 2026-01-09 | 2026-04-19 | High | Ironclad Finance | Mobile, GDPR, SEO | Roll-forward migration plan drafted.
PRJ-005 | Lumina Retail Checkout 2.0 | Elif D. | Release | on_track | 76 | 2026-01-19 | 2026-05-03 | High | Lumina Retail | Onboarding, React, Mobile | Waiting on content from client marketing team.
PRJ-006 | Vertex Analytics Pipeline | Aya M. | Live | on_track | 100 | 2025-12-14 | 2026-03-25 | Low | Vertex Analytics | API, Mobile | Awaiting stakeholder approval.
PRJ-007 | Polaris Media CMS Migration | Marcus T. | Live | on_track | 100 | 2025-12-11 | 2026-02-18 | Medium | Polaris Media | Internal, Migration, React
PRJ-008 | Glider Logistics Tracker | Sarah K. | Development | on_track | 56 | 2026-04-28 | 2026-06-05 | Medium | Glider Logistics | Internal, B2B, SEO
PRJ-009 | Aster Robotics Control Panel | Ravi S. | Development | on_track | 40 | 2026-03-31 | 2026-06-23 | High | Aster Robotics | Realtime, Migration, API | Designs signed off — implementation in progress.
PRJ-010 | Brightwave Edu LMS | Diego N. | QA | on_track | 77 | 2026-03-16 | 2026-05-08 | Medium | Brightwave Edu | Analytics
PRJ-011 | Cascade Energy Billing Rewrite | Marcus T. | Release | at_risk | 77 | 2026-03-17 | 2026-07-02 | Medium | Cascade Energy | Multi-tenant, Dashboard, Onboarding | Smoke tests passing on staging.
PRJ-012 | Delphi Legal Contract AI | Nora W. | Development | at_risk | 24 | 2026-03-02 | 2026-06-25 | High | Delphi Legal | SEO, B2C, Migration | Smoke tests passing on staging.
PRJ-013 | Helios Solar Monitor | Aya M. | Live | at_risk | 100 | 2026-03-03 | 2026-04-10 | Medium | Helios Solar | AI, React | Localization pending for 3 markets.
PRJ-014 | Kestrel HR Onboarding | Maya P. | QA | delayed | 44 | 2026-05-09 | 2026-08-04 | Low | Kestrel HR | Migration, E-commerce | Load testing in progress.
PRJ-015 | Lotus Hospitality Booking | Aya M. | QA | on_track | 61 | 2026-03-02 | 2026-04-08 | Medium | Lotus Hospitality | GDPR | Client requested scope additions.
PRJ-016 | Meridian Bank Open API | Nora W. | Release | at_risk | 87 | 2026-01-02 | 2026-03-30 | High | Meridian Bank | API, Multi-tenant
PRJ-017 | Northwind Inventory Sync | Zoe F. | QA | delayed | 63 | 2026-02-27 | 2026-06-24 | Medium | Northwind Co. | API | Third-party API rate limits being reviewed.
PRJ-018 | Onyx Insurance Claims Portal | Ravi S. | Development | on_track | 20 | 2026-03-10 | 2026-05-08 | Low | Onyx Insurance | Dashboard, Payments, API | Waiting on content from client marketing team.
PRJ-019 | Quartz Gaming Leaderboards | Liam O. | Development | at_risk | 56 | 2026-04-07 | 2026-07-24 | Medium | Quartz Gaming | B2C | Awaiting stakeholder approval.
PRJ-020 | Rivet Manufacturing IoT | Zoe F. | Planning | at_risk | 14 | 2026-05-12 | 2026-07-31 | Medium | Rivet Mfg. | B2B | Roll-forward migration plan drafted.
PRJ-021 | Stellar Telecom Self-Service | Priya R. | Release | on_track | 89 | 2026-03-02 | 2026-04-27 | High | Stellar Telecom | SEO | Awaiting stakeholder approval.
PRJ-022 | Tidepool Fitness App | Marcus T. | Planning | on_track | 19 | 2026-01-20 | 2026-03-10 | Low | Tidepool Inc. | E-commerce, AI | Designs signed off — implementation in progress.
PRJ-023 | Umbra Security Audit Tool | Elif D. | Live | at_risk | 100 | 2026-02-07 | 2026-04-10 | Low | Umbra Security | B2B, Mobile | Third-party API rate limits being reviewed.
PRJ-024 | Vanta Compliance Sync | Priya R. | Release | at_risk | 77 | 2026-05-02 | 2026-07-10 | Medium | Vanta | SEO | Localization pending for 3 markets.
PRJ-025 | Willow Gardens Store | Nora W. | QA | at_risk | 61 | 2026-03-19 | 2026-04-20 | Low | Willow Gardens | API, E-commerce
PRJ-026 | Xenon Travel Itineraries | Liam O. | QA | delayed | 51 | 2026-01-29 | 2026-04-02 | Low | Xenon Travel | Migration | Designs signed off — implementation in progress.
PRJ-027 | Yonder Social Feed | Elif D. | Live | delayed | 100 | 2025-12-20 | 2026-04-10 | Medium | Yonder | GDPR | Client requested scope additions.
PRJ-028 | Zephyr Auto Service Hub | Sarah K. | Development | on_track | 21 | 2026-05-06 | 2026-07-20 | Medium | Zephyr Auto | B2B, Payments | Designs signed off — implementation in progress.
PRJ-029 | Cobalt Studio Portfolio | Marcus T. | Live | at_risk | 100 | 2026-01-26 | 2026-04-10 | Low | Cobalt Studio | Mobile | Designs signed off — implementation in progress.
PRJ-030 | Ember Podcast Platform | Elif D. | Release | on_track | 94 | 2026-03-05 | 2026-06-04 | High | Ember Media | B2B | Roll-forward migration plan drafted.
PRJ-031 | Fable Reader App | Zoe F. | QA | delayed | 64 | 2026-02-14 | 2026-03-31 | Low | Fable | Internal, B2B, Realtime | Security review scheduled for next week.
PRJ-032 | Gemstone Marketplace | Zoe F. | Release | delayed | 69 | 2026-03-15 | 2026-06-03 | High | Gemstone | AI, Dashboard, B2C | Security review scheduled for next week.

## README
Stresk Dashboard — Data Template
How to publish this sheet to your dashboard:
1. Upload this file to Google Drive and open with Google Sheets.
2. File → Share → Publish to web.
3. Choose the 'Projects' tab, format = Comma-separated values (.csv).
4. Click Publish and copy the generated URL.
5. In the dashboard repo, open src/config.js and paste the URL into CONFIG.SHEET_URL.
6. Reload the dashboard — the 'mock' pill in the header switches to 'sheet'.
Column rules:
• project_id — any unique string (e.g. PRJ-001).
• stage — one of: Planning, Development, QA, Release, Live.
• status — one of: on_track, at_risk, delayed.
• progress — integer 0–100.
• start_date / release_date — use YYYY-MM-DD.
• priority — one of: High, Medium, Low.
• tags — comma-separated list inside a single cell.
The dashboard auto-computes OVERDUE / AT-RISK / STALLED alerts from these fields.